# NeuralFieldManifold (Submission 32988) — Rebuttal Plan

Window: Jul 25–31, 2026. Per-reviewer limit: 10,000 characters, markdown tables only, no files/links/figures. AC's 3 pre-rebuttal flags: (1) torus-from-Takens not novel, (2) mouse EEG doesn't convincingly show toroidal structure, (3) sparse-K-sinusoid assumption too stringent.

## Priority ranking of the 4 runnable analyses

Ranked by (impact on AC's 3 flags + number of reviewers it satisfies) ÷ (effort/risk):

1. Session/subject-disjoint CV on sleep decoding — do this first. Cheapest of the four (rerun on existing mouse EEG data, no new recordings), and it's the single most-cited weakness: UV2Y Q1, XUiw Q5, and tSve Q3 all independently ask for it, and your own pre-submission .tex comments already flagged "no CV, no error bars" as an open TODO. High certainty of a clean result in a few hours.

2. Betti recovery split by order-correct vs order-incorrect windows — do this second. This is a re-slice of data you likely already have in memory (you already compute per-window AR order estimates and per-window Betti vectors for the monkey V1 windowed persistence analysis). Almost free, and it directly answers tSve Q1 while also giving you real ammunition for AC concern #2: if the (1,1,1)-vs-(1,2,1) split correlates with order-recovery errors rather than genuine single-mode windows, that changes the whole interpretation of "only 46%."

3. Frequency-separation sweep (synthetic) — do this third. Fully synthetic, so zero data-availability risk, and it's the most direct possible answer to AC concern #3 (the sparse-K-sinusoid assumption). Moderate effort: generate 2-oscillator AR signals across a grid of Δω, rerun the existing reconstruction + Betti pipeline, record where recovery degrades.

4. Raw delay embedding + persistent homology without DeepLagField — do this fourth, or drop it. Answers only one reviewer (XUiw Q3), and OLS-based coefficients are already computed as a baseline in Table 1, so the marginal work is mostly rerunning persistent homology on the OLS-based embedding instead of the DeepLagField one. Useful but lowest yield of the four — first thing to cut if the week gets tight.

Stretch goal (your call, per your answer): reaching-task dataset for a "clean torus + real behavioral label" decode. This is what reviewer aNy5 (your most positive reviewer, 4/borderline-accept) suggested — apply the framework to motor-cortex reaching data (Churchland et al., Nature 2012). If it works, it's the single strongest rebuttal to AC concern #2, because it would show behaviorally-relevant decoding on a dataset that scores as a genuine torus (unlike mouse EEG), directly answering UV2Y Q1 ("does the decoding gap survive on a clean-torus dataset?"). But it's new-dataset risk: acquiring + preprocessing + running the full pipeline (order selection → embedding → torus fit → decode reach direction/onset from torus params) in ~1-2 days is tight. Flagged as Table 5 below — attempt after 1-4 are safely done, and if it doesn't converge cleanly, fall back to the qualitative/camera-ready promise per your instruction.

## Zero-risk items — no new data needed, can finalize now

Table 3 wording fix. The compiled PDF's Table 3 (tab:related_work_compact) labels your contribution "K-torus (proven)." UV2Y quotes this word directly as an overclaim, and they're right — Proposition B.5 only proves the result in the noiseless, marginally-stable limit, which real recordings violate. Fix: change the table cell to "K-torus (derived; noiseless limit)" and add one clarifying clause in the caption. This costs nothing and removes a real, citable overclaim before a reviewer has to keep bringing it up.

Novelty framing (AC concern #1 / aNy5's weaknesses). aNy5 and UV2Y both point out that "oscillations ⇒ torus" is a known consequence of Takens + linear systems theory (citing a Neuromatch Academy 2020 tutorial and Chaudhuri et al. 2019). This is factually fair — you should concede the qualitative topological fact is not new, and redirect to what actually is new: (a) predicting K prospectively from spectral peak count rather than inferring it post-hoc from population activity (unlike Gardner 2022's grid-cell tori, which are fit to already-collected data with no predictive claim), (b) the TVAR local-stationarity bound with a quantified error rate for nonstationary signals, (c) delay embeddings resolving spectrally-overlapping modes that the PSD cannot distinguish (Appendix A.4) — a testable, falsifiable claim, not just an application of Takens. Conceding the qualitative point while defending the predictive/quantitative contribution is a stronger rebuttal than disputing novelty outright.

## Table skeletons — fill in real numbers as analyses finish

### Table 1 (→ UV2Y Q1, XUiw Q5, tSve Q3) — Sleep decoding with proper CV

| Split | Features | F1 (mean ± SD) | Baseline F1 (mean ± SD) | n sessions/animals held out |
| --- | --- | --- | --- | --- |
| Session-disjoint CV | Torus (R1, R2, r) | [TODO] | [TODO] | [TODO] |
| Subject-disjoint CV | Torus (R1, R2, r) | [TODO] | [TODO] | [TODO] |

State the baseline explicitly in the caption (which multi-band spectral features, which classifier) — reviewers flagged "a baseline that is never specified" by name.

### Table 2 (→ tSve Q1, AC #2) — Betti recovery vs. order-recovery accuracy (monkey V1)

| Window group | % of windows | Betti = (1,2,1) | Betti = (1,1,1) | Betti = other |
| --- | --- | --- | --- | --- |
| Order estimate correct (p̂=4) | [TODO] | [TODO] | [TODO] | [TODO] |
| Order estimate off by ±1 | [TODO] | [TODO] | [TODO] | [TODO] |
| Order estimate off by >1 | [TODO] | [TODO] | [TODO] | [TODO] |

If (1,1,1) concentrates in the order-wrong rows, that's a strong, honest answer to "does the 40% mean the method misses the second oscillation."

### Table 3 (→ AC #3, tSve Q2) — Frequency-separation sweep (synthetic, 2-oscillator AR)

| Δω (rad/sample) | Betti = (1,2,1) recovery rate | Torus score | Torus error |
| --- | --- | --- | --- |
| 0.50 | [TODO] | [TODO] | [TODO] |
| 0.25 | [TODO] | [TODO] | [TODO] |
| 0.10 | [TODO] | [TODO] | [TODO] |
| 0.05 | [TODO] | [TODO] | [TODO] |
| 0.02 | [TODO] | [TODO] | [TODO] |

Report the Δω at which recovery rate drops below (say) 80% as your stated "minimum resolvable separation" — gives reviewers a concrete number instead of a qualitative limitation.

### Table 4 (→ XUiw Q3) — Torus recovery with vs. without DeepLagField

| Method | Betti = (1,2,1) rate (Monkey V1) | Torus score | Order source |
| --- | --- | --- | --- |
| DeepLagField (full pipeline) | 46% (reported) | [TODO] | learned, time-varying |
| Raw OLS delay embedding, fixed p=4 | [TODO] | [TODO] | fixed, from PSD peak count |

Shows whether the toroidal signature is a property of the raw signal or an artifact of the reconstruction network.

### Table 5 (stretch) — Reaching-task decode on a clean-torus dataset

| Dataset | Procrustes disparity (torus validity) | Decode target | Torus-feature F1 | Spectral-baseline F1 |
| --- | --- | --- | --- | --- |
| Mouse EEG (existing) | 0.4092 (spurious range) | Sleep stage | 74% (reported) | 60% (reported) |
| Reaching task (new) | [TODO — should be well below 0.0820 true-torus threshold] | Reach direction / onset | [TODO] | [TODO] |

This table is the whole rebuttal to AC concern #2 in one row: if it lands, you've shown the decoding advantage survives precisely where the geometry is real, which directly neutralizes UV2Y's "useful exactly where the metric says it isn't a torus" critique.

## Zero-cost supporting table — ready now, no new data

### Table A (→ UV2Y weakness #1, AC #2) — Geometric validity is graded, not binary

| Dataset | Procrustes disparity | True-torus threshold | Spurious-bulk region | Interpretation |
| --- | --- | --- | --- | --- |
| Monkey V1 LFP | 0.1477 | 0.0820 | — | Above true-torus threshold, well below spurious bulk: valid geometry, moderate noise |
| Mouse hippocampus LFP | (check your data — not stated in main text, pull if available) | 0.0820 | — | — |
| Mouse cortex EEG | 0.4092 | 0.0820 | within spurious-torus distribution | Weakest narrowband peak of the three; diagnostic correctly grades it as noisier |

All numbers already exist in Appendix L — this just repackages them into one glance-able table for the rebuttal, framing the mouse-EEG score as the expected low end of a continuous scale rather than a binary failure.

## Next step

Once you have real numbers for Tables 1–4 (and 5 if it converges), send them back and I'll draft the four per-reviewer rebuttal texts (UV2Y, aNy5, XUiw, tSve), each under 10,000 characters, built around whichever tables are most relevant to that specific review.